## Command Center
ScholarPath Build Command Center
Invite-only beta ¦ Target: 14 August 2026 ¦ Updated: 6 August 2026
Metric | Live value | TODAY - CLOSE B01 FIRST
Calendar days remaining | 8 | Blocker | Supabase authentication and project access
Modules blocked | 2 | Owner | Haidar
Modules partial | 11 | Why first | Database, Auth, live recommendations and operations depend on it
Modules deferred | 3 | Haidar action | Complete Supabase sign-in
Open P0 blockers | 7 | Codex next | Apply 009-010, configure preview and run live acceptance
Release gates done | 0 | Deadline | 6 August 2026
Current opportunities | 5
LAUNCH BOUNDARY
Ship | Auth, profile, data truth, eligibility, recommendations, discovery, basic tracking and feedback
Optional | Document upload only after private storage passes
Defer | Writing, recommenders, offers, iOS, full rankings, semantic search and automation
Audience | 5-10 controlled testers; not a public launch

## Daily Sprint
ScholarPath Eight-Day Sprint
6-14 August 2026 ¦ One release outcome per day
Date | Delivery | Owner | Status | Blocked by | Exit test | Notes
2026-08-06 | Restore Supabase; apply 009-010; configure secrets | Haidar + Codex | Blocked | B01 | Live database and protected preview start | Highest priority
2026-08-07 | Configure Auth, first admin and roles | Haidar + Codex | Blocked | B01 | Two unrelated students pass isolation
2026-08-08 | Connect profile to eligibility and recommendations | Codex | Partial | B02-B03 | One student receives stored explainable results
2026-08-09 | Add and review opportunities 6-8 | Codex + Reviewer | In Progress | B04 | Every fact has official evidence
2026-08-10 | Add opportunities 9-10 and 30 golden profiles | Codex + Reviewer | In Progress | B04-B05 | Regression and subgroup review pass
2026-08-11 | Verify portfolio to application to tasks | Codex | Partial | B02-B05 | Recommendation becomes persistent plan
2026-08-12 | Mobile, accessibility, errors, feedback and monitoring | Haidar + Codex | Not Started | B06 | No P0 defect; failures observable
2026-08-13 | Freeze, smoke, backup/rollback and invitations | Haidar + Codex | Not Started | B07 | Release candidate approved
2026-08-14 | Invite 5-10 controlled testers | Haidar | Not Started | All P0 | Monitor onboarding and corrections | Invite-only beta

## Module Register
ScholarPath Module Register
Verified status and exact launch blockers ¦ Updated 6 August 2026
ID | Module | Status | Beta decision | What exists | Blocking / missing | Owner | Due | Next action
M00 | Design system and shell | Partial | Ship | Urbanist, responsive shell, states and accessibility foundations | Founder sign-off and live desktop/mobile check | Haidar | 2026-08-13 | Approve UI and close P0 defects
M01 | Account, consent and security | Blocked | Must ship | Auth UI, middleware, roles, consent schema and RLS | Supabase keys, redirects, first admin, recovery and two-user isolation | Haidar + Codex | 2026-08-07 | Complete Supabase login and Auth setup
M02 | Profile and evidence | Partial | Must ship | Guided profile, validation, normalization and snapshots | Live persistence and signed-in completion test | Codex | 2026-08-08 | Run live profile acceptance
M03 | Education truth system | Partial | Must ship | Versioned sources, facts, rules, 4 countries, 9 cities and 12 institutions | Deploy 009-010 and review five more opportunities | Codex + Reviewer | 2026-08-10 | Publish opportunities 6-10
M04 | Eligibility engine | Partial | Must ship | Deterministic gates, conditional/unknown states and reason codes | Production catalogue regression and golden profiles | Codex | 2026-08-10 | Run 30-profile suite
M05 | Recommendation engine | Partial | Must ship | Versioned scoring, explanations, balance and persistence model | Golden/fairness suite and live stored runs | Codex | 2026-08-10 | Store and compare live runs
M06 | Discovery and details | Partial | Must ship | Search, filters, citations, freshness and live API boundary | Ten live opportunities and production acceptance | Codex | 2026-08-10 | Verify live discovery
M07 | Portfolio and compare | Partial | Ship basic | Save, grouping, notes and comparison UX | Live persistence against recommendation versions | Codex | 2026-08-11 | Test save and compare
M08 | Application tracker | Partial | Ship basic | Application states, requirements, readiness and activity | One complete live application journey | Codex | 2026-08-11 | Create one live application
M09 | Tasks and deadlines | Partial | Ship basic | Kanban, impact, dependencies, evidence, APIs and tests | Live task generation and deadline acceptance | Codex | 2026-08-11 | Generate and move live tasks
M10 | Document vault | Partial | Optional | Private buckets, RLS and upload/download routes | Live signed-storage test or disable beta upload | Codex | 2026-08-12 | Prove private access or disable
M11 | Notifications and support | Partial | Feedback only | Preferences, corrections and outbox models | Working feedback channel and monitoring | Haidar + Codex | 2026-08-12 | Activate feedback and alerts
M12 | Operations and admin | Blocked | Must ship | Protected API, UI, audit and research roles | Production admin, source-review exercise and advisors | Haidar + Codex | 2026-08-12 | Create admin and run review
M13 | Writing and recommenders | Deferred | After beta | Foundation UI, routes and confidential-storage model | Email, reminders and submission acceptance | Codex |  | Do not work before launch
M14 | Funding and offers | Deferred | After beta | Planning UX and data model | Live offer and decision workflow | Codex |  | Do not work before launch
M15 | Shared API and iOS | Deferred | After beta | Reusable server routes and domain services | Versioned v1, OpenAPI and iOS client | Codex |  | Do not work before launch

## Blockers
ScholarPath Blocker Register
P0 blockers controlling the 14 August invite-only beta
ID | Blocker | Priority | Owner | Due | Status | Impact | Next action
B01 | Supabase authentication and project access | P0 | Haidar | 2026-08-06 | Blocked | All live database, Auth and operations work | Sign in to Supabase
B02 | Apply migrations 009-010 and secure environment values | P0 | Codex | 2026-08-06 | Blocked | Production catalogue and permission matrix | Close B01
B03 | Auth redirects, first admin and two-user isolation | P0 | Haidar + Codex | 2026-08-07 | Blocked | Signed-in beta and staff operations | Close B01
B04 | Five additional independently reviewed opportunities | P0 | Codex + Reviewer | 2026-08-10 | In Progress | Catalogue breadth and recommendation proof | Review official sources
B05 | Thirty golden profiles and signed-in end-to-end test | P0 | Codex | 2026-08-11 | In Progress | Decision correctness and critical journey | Build fixtures and test
B06 | Feedback, monitoring and release alerts | P0 | Haidar + Codex | 2026-08-12 | Not Started | Beta support and observability | Choose channels and configure
B07 | Founder desktop/mobile approval | P0 | Haidar | 2026-08-13 | Not Started | Final release sign-off | Review release candidate

## Beta Gates
ScholarPath Beta Gates
The beta stays closed until every P0 condition has evidence
Gate | Release condition | Priority | Status | Blocked by | Acceptance evidence
G01 | Production Supabase and Vercel connected | P0 | Blocked | B01-B02 | No demo mode in live environment
G02 | Auth and tenant isolation | P0 | Blocked | B01-B03 | Two students and staff roles pass
G03 | Ten reviewed opportunities | P0 | In Progress | B04 | Current evidence and independent review
G04 | Thirty golden profiles | P0 | In Progress | B05 | Regression and subgroup review pass
G05 | Critical student journey | P0 | Partial | B02-B05 | Auth-profile-recommendations-portfolio-application-tasks
G06 | Trust and explanations | P0 | Partial | M03-M05 | Sources, uncertainty and next actions visible
G07 | UX and accessibility | P0 | Not Started | B07 | Founder desktop/mobile approval
G08 | Support and monitoring | P0 | Not Started | B06 | Feedback and errors reach team
G09 | Release safety | P0 | Not Started | All P0 | No critical defect; backup and rollback checked